## Sheet1
Accelerated Failure Time Models | Implement Gradient , Hessian | AFT | Log-logistic | Documentation | 5/6/2019 - 5/26/2019 | Community Building
|  |  | Log-Normal |  | 5/27/2019 - 6/24/2019 | Phase 1 | AFT Lognormal
|  | Binomial | Count Upper Bound |  | 6/25/2019 - 07/22/2019 | Phase 2 | AFT Log Logistic
[5 empty] | 07/26/2019 - 08/19/2019 | Phase 3 | Binomial Count
[5 empty] | 08/20/2019 - 08/26/2019 | Students continue working on their project with guidance from Mentors | Future Scope

## Sheet2
|  |  | 2017-05-01 |  | 2019-06-01 |  | 2019-07-01 |  | Aug
Phase | Purpose | Days | 6 | 26 | 9 | 24 | 9 | 22 | 9 | 19 | 28
Community Bonding | Roadmap Discussion | 21
1st Half - Phase 1 | Implement AFT - Log-Normal | 14
2nd Half - Phase 1 | Documentation and Testing of AFT - Log-Normal | 14
1st Half - Phase 2 | Implement AFT - Log-Logistic | 15
2nd Half - Phase 2 | Documentation and Testing of AFT - Log-Logistic | 13
1st Half - Phase 3 | Implement Binomial loss - upper bound trials | 18
2nd Half - Phase 3 | Documentation and Testing of Binomial loss - upper bound trials | 10
Final Evaluation | Produce relevant documents , blogs and discuss future plans | 9